## 00_READ_ME
Item | Detail
Status | ARTEFACT PATCH — 28 September 2026. Supersedes nothing; add these rows to the existing subsheets.
Scope | Artefact and code integrity only. No citation, no chapter argument and no reported figure changed.
Trigger | Committing the Synthea subset to GitHub exposed that the public repository was ahead of the working set.
Reported figures | Unchanged and re-verified: 90/200 records, 95 violations, 39 Corollary 1.2 witnesses, 138 invalidations, 0 under Semantics II, commitment 11087780fd192c8f, mean payload 891 bytes (8-bundle subset) and 1,006 (full cohort).
Verification method | Fresh clone of github.com/Astheno-sphere/TRF, then run. Not a working-copy run.

## 01_THIS_ROUND
ID | Item | Resolution | Where
R-01 | Repository shipped no dataset, so demo Tab 3 showed 'no bundles found' | 8 untrimmed Synthea bundles committed to data/synthea_subset/ (40 MB) | GitHub repo; repro_package/data/; code_artefacts/
R-02 | requirements.txt, docs/expected_trf_output.txt and norwegian_docs/HOW_TO_RUN.md absent from the repository | Restored. The first two reproduce the md5 values CHECKSUMS.md had recorded, so the 23 Sept web upload had dropped them | GitHub repo
R-03 | docs/Appendix_A.md and norwegian_docs/NORWEGIAN_MODULE_README.md sat at the repository root under other names | Moved to the paths README.md references; contents byte-identical | GitHub repo
R-04 | Trail entries D-05, A-04, A3-l and P8-03 recorded as applied were present ONLY in the pushed copy | Working set brought onto the repository version: checker 362 to 363 lines with the Ch4 §4.8 salt destruction, layer gains the three-directory fallback | demo_app/, repro_package/, code_artefacts/, outputs root
R-05 | Appendix A repeated a FALSE claim: 'the code states in a comment that production deployments must use a CSPRNG'. grep CSPRNG over the source returns nothing | Replaced by an accurate statement of the salt's reproducibility-only status, in all four copies AND the assembled submission, which still carried it | App A §A.4; Ch-level: none
R-06 | Appendix A stated 'Line count: 362' and described three trimmed sample bundles that no longer ship | Corrected to 363 and to the eight untrimmed bundles; the 891 vs 1,006 statement added | App A §A.1b, §A.5, §A.8
R-07 | Appendix A contents table listed norwegian/norwegian_layer.py; both modules sit at the repository root | Path prefix dropped in all four copies and the submission | App A §A.1b
R-08 | Reproducibility package could not run its own realism layer: the layer resolves its data directory relative to its own file, so from src/ it looked for src/data/synthea_subset/ | Modules moved to the package root; run_all.sh rewritten to four steps and no longer gated on the 314 MB cohort | repro_package/
R-09 | Norwegian modules under src/norwegian/ could not import trf_checker | Moved to the package root alongside the checker | repro_package/
R-10 | run_all.sh told the reader the Synthea diff should be byte-identical; it cannot be, because the recorded run was the 98-bundle cohort and the package ships 8 | Both runs now recorded separately: synthea_comparison_subset_output.txt and synthea_comparison_full_cohort_output.txt | repro_package/results/
R-11 | VERSION_REGISTER Words column read about 4 per cent high across all rows | Recomputed as len(text.split()) and the method stated in the register. Submission is 50,667 by that measure, 50,486 by wc -w, not 52,567. The md5 column was accurate throughout | VERSION_REGISTER.md

## 02_FETCH_REGISTER
ID | Item | Status | Note
F-02 | EDPB CEF full report | OPEN | Not load-bearing; recurring-issue count deliberately removed
F-05 | Haque venue | OPEN | Belen-Saglam attribution already corrected; venue confirmation outstanding
— | aiAuthZ, arXiv 2607.05518 | OPEN | For Ch2 §2.4 as converging practice
— | Privacy Engineering SLR, arXiv 2606.23696 | OPEN | For Ch2 §2.4 or Ch6
— | Finck 2019 EP study DOI | OPEN | One of four DOIs outstanding
— | Staffa et al. 2018 DOI | OPEN
— | Scope et al. JDI 2022 DOI | OPEN
— | Scope & Rasin patent DOI | OPEN
— | Zenodo DOI for the repository | OPEN | Mint after the artefact stops moving

## 03_DELIVERABLES
Artefact | Detail | Status
github.com/Astheno-sphere/TRF | Three commits on 28 Sept: subset plus repair, Appendix A path fix, trail and checksums | LIVE AND VERIFIED FROM A FRESH CLONE
data/synthea_subset/ | 8 untrimmed bundles, 40 MB, with a provenance README carrying the six Synthea markers | COMPLETE
docs/expected_trf_output.txt | The recorded checker run, for the reader to diff against | COMPLETE — md5 41b56742d35d
norwegian_docs/HOW_TO_RUN.md | Step-by-step guide. REWRITTEN, not recovered: the 116-line original was never uploaded and no copy survives | COMPLETE — 103 lines, differs from the lost original
repro_package/ | Flattened; bash run_all.sh exits clean on all four steps | COMPLETE
VERA-SNARK_Thesis_SUBMISSION.md | Appendix A replaced with the corrected version; 2,550 lines | REASSEMBLED — md5 c2529689892b
VERSION_REGISTER.md | 29 registered files, all checksums verified matching | RECONCILED 28 Sept
trfhimolde.streamlit.app | Redeploys from the new commit | AWAITING YOUR CONFIRMATION — open Tab 3, run the layer, expect 891 bytes

## 04_OUTSTANDING
Item | Priority | Note
Confirm Streamlit Tab 3 shows 891 bytes | HIGHEST | If it prints anything else, Chapter 5 follows the committed cohort, never the reverse
Send Joao the update email | HIGH | The data blocker is now answerable with a link he can clone and run
Sikt notification for the expert evaluation | HIGH | You reversed the earlier decision and want the evaluation run
Read and integrate aiAuthZ and the privacy-engineering SLR | MEDIUM | Two discovered sources, still unread
Four DOIs | MEDIUM | Finck 2019, Staffa 2018, Scope JDI 2022, Scope & Rasin patent
Zenodo DOI | MEDIUM | After the repository settles
Two figures | MEDIUM | Regulatory timeline §6.8; record-state diagram §4.8 reprised §5.6
HiMolde template | MEDIUM | Site blocks automated fetch; you download it, then a format pass
Datatilsynet informal sounding | LOW | Would strengthen §6.2 and §7.4
Viva notes, five hard questions | LOW | Where is the logistics; do access logs count as data within the environment; are 1-12-month permits realistic; Semantics II has no authority; why informal proofs
NORS 2025 notice | LOW | Your call with Joao

## 05_INTEGRITY_LESSON
Finding | Detail
What went wrong | Four change-trail entries were marked applied but existed only in the copy pushed to GitHub. The working set, the reproducibility package and the assembled submission all still carried the pre-correction text, including one claim D-05 had removed as demonstrably false.
Why it was not caught | Reconciliation diffed files within the working set against each other and against an archive. It never diffed them against the public repository, which was the newest copy.
Standing fix | Every future reconciliation clones the public repository and diffs against it. A trail entry marked applied is a claim to check, not a fact.
What it cost | Nothing reported changed. The risk was reputational: a reader who cloned the repository and read the submission would have found the appendix describing a 362-line file that is 363 lines, and asserting a code comment that does not exist.