## 00_READ_ME
Item | Detail
Status | FINAL PATCH — 16 Sept 2026. Supersedes PATCH1/2/3 and MASTER. Copy each tab as one block.
Thesis state | All 7 chapters + front matter + Appendix A complete. Assembled full document produced.
Measured words | Front 2,057 ¦ Ch1 4,744 ¦ Ch2 11,107 ¦ Ch3 4,449 ¦ Ch4 6,958 ¦ Ch5 3,270 ¦ Ch6 4,209 ¦ Ch7 2,083 ¦ AppA 1,412 ¦ TOTAL ~40,300 (~89pp)
Page issue | 89pp vs Joao's 80pp ceiling. Ch2 is the overrun. See tab 05.
Deliverables added | Consolidated_Bibliography.Rmd (67 entries, chapter-tagged); repro_package/ (self-verifying, byte-identity PASS)

## 01_THIS_ROUND
ID | Item | Resolution | Where
CORR-028 | Ch5 had NO reference section while citing Synthea and basisprofiler | Reference section added (Walonoski 2018; HL7 Norway 2025); in-text citations inserted at first mention | Ch5 §5.2, §5.7, refs
CORR-029 | Ch1 cited '(NIST, 2025)' but reference entry is 'National Institute of Standards and Technology' | In-text harmonised to full name. Found by programmatic citation audit, not by eye | Ch1 §1.3
CORR-030 | F-06 unresolved (TEHDAS2 deliverable number) | RESOLVED: D7.4 'Technical specification for health data access bodies on the implementation of secure processing environments'. Also confirmed D7.2 (minimisation/pseudonymisation/anonymisation/synthetic data) and D6.3 | Ch2, Ch3, Ch4, Ch6
CORR-031 | Theorem 2 vulnerable to 'you defined your way out' objection | Candour passage added: concedes the mathematical content is modest and the proof is verification not discovery; states Theorem 1 carries the load; Semantics II defensibility argued in §4.2, authority confronted in §6.2 | Ch4 §4.7
CORR-032 | Art 68(12) broad reading asserted as fact (SELF-CAUGHT FALLACY) | Proposal Art 46(9) text reads 'The data within the secure processing environment shall be deleted within 6 months' — broad by location but sits in the data-permit article. Now stated as contestable, with a map of what depends on it: Cor 1.2 only; Thm 1, Cor 1.1, Thm 2, mechanism, residue all unaffected | Ch1, Ch2, Ch4 §4.6, Ch5 §5.4, Ch6 §6.2, Ch7 §7.4
CORR-033 | Front matter did not exist in rebuild; old draft's abstract/IRB claim still attached | Written fresh: abstract (520w, states limitations in the abstract), contribution statement with 'What is not claimed', ethics declaration WITHDRAWING the IRB claim by name, AI-assistance declaration, full nomenclature (model symbols + 27 abbreviations), TOC | Front_Matter_v1.md

## 02_FETCH_REGISTER
ID | Item | Status | Note
F-01 | SPUHiN D5.2 full PDF | OPEN | Checklists verified; §6.6 absence claim already stated at reduced strength because of this
F-02 | EDPB CEF Art-17 full report | OPEN | Recurring-issue count deliberately removed rather than guessed
F-03 | EDPB Guidelines 02/2025 status | RESOLVED | v2.0 adopted 7 July 2026 after consultation — confirmed at edpb.europa.eu. Strengthens §4.9: metadata+content are in principle personal data, may extend to encrypted/hashed
F-04 | Aikebaier SoK | RESOLVED | Open problem #5 = our gap; #4 (ZKP selective disclosure) = our future work
F-05 | Haque et al. final venue | OPEN | arXiv cited; venue unconfirmed
F-06 | TEHDAS2 SPE deliverable number | RESOLVED | D7.4
F-07 | Albalwy full PDF | OPEN (optional) | Only if 113ms figure used; currently not
F-08 | EHDS implementing acts | RESOLVED | Art 73(5): due by 26 Mar 2027, not adopted
F-09 | Walonoski Synthea citation | RESOLVED | JAMIA 25(3):230-238 exact
F-10 | eHOMB '12 March' year | OPEN | Source has no year; chapters state date without asserting year
F-11 | EUR-Lex verbatim Art 73(1)(e) | SUBSTANTIALLY CORROBORATED | Full Art 73(1)(a)-(f) retrieved from two independent reproductions; official EUR-Lex text fetch returns page chrome
F-12 | EHDS in-force vs applies-from | RESOLVED | In force 26 Mar 2025; applies 26 Mar 2027; secondary use (Ch IV incl. Arts 68, 73) 26 Mar 2029

## 03_DELIVERABLES
Artefact | Detail | Status
Front_Matter_v1.md | Title, abstract, contribution statement, declarations, nomenclature, TOC | COMPLETE
Chapter1-7 (7 files) | Individually maintained, cross-referenced, anti-drift swept | COMPLETE
VERA-SNARK_Thesis_FULL_16Sept2026.md | Assembled: front matter + 7 chapters + Appendix A | COMPLETE
Consolidated_Bibliography.Rmd | 67 unique entries, de-duplicated across 7 chapter lists, alphabetised, chapter-provenance tagged, APA 7. Source-type flags (preprint/patent/commentary/guidance) visible in the list itself | COMPLETE
repro_package/ | README + run_all.sh + src/ + data/synthea_sample/ + results/ + docs/Appendix_A.md. Executed end-to-end; rerun byte-identical to reported run (PASS) | COMPLETE & SELF-VERIFIED
Citation audit | Programmatic: every in-text (Author, year) matched against reference entries. 2 defects found and fixed (CORR-028, CORR-029) | COMPLETE

## 04_OUTSTANDING
Item | Priority | Note
Send Joao the update email | HIGHEST | Drafted, unsent. He has seen none of this. Highest-risk item on the project and unrelated to the text
Viva preparation notes | HIGH | Nothing exists. 5 questions: where's the logistics; are access logs 'data within the environment'; are 1-12mo permits realistic; Semantics II has no authority; why informal proofs
Chapter 2 reduction | HIGH | 89pp vs 80pp ceiling. Ch2 = 11,107w. Cut targets: §2.2 and §2.7 background that Ch4/Ch6 restate; also the absence-of-literature argument leans harder than it should given provisions apply 2029
Remaining fetches F-01/F-05/F-10/F-11 | MEDIUM | Half a day, one sitting, none load-bearing
Two figures | MEDIUM | Timeline (2025 in force -> 2027 acts -> 2029 secondary use); record-state diagram (payload -> commitment + invalidation + auditor view)
Formatting / Rmd / PDF | LAST | Only after content freeze

## 05_CH2_OVERRUN
Section | Words (approx) | Assessment
NOTE |  | 'Overrun' = Ch2 is ~11,100 words against a planned ~7,000-8,000, and the thesis total is 89pp against Joao's 80pp ceiling. Ch2 is where the excess sits.
2.1 Review Strategy | ~600 | Keep
2.2 Cross-Border Landscape | ~1,500 | CUT CANDIDATE — Ch1 §1.1 and Ch4 §4.11 restate much of the MyHealth@EU/NCPeH detail
2.3 Retention vs Erasure Tension | ~2,400 | KEEP — carries Art 17(3)(b) defence, Art 73(1)(e), legal corridor. Load-bearing
2.4 Cryptographic Approaches | ~2,600 | TRIM — comparator paragraphs (Health-zkIDM, zkFL-Health, NewbornTime) could compress; prior-art and PoSE passages must stay
2.5 Formal Approaches | ~700 | KEEP — anchors the method
2.6 Norwegian Infrastructure | ~1,200 | KEEP — the substrate argument
2.7 Information Logistics | ~800 | CUT CANDIDATE — the maritime example and OECD figures are colour; the customs-ledger analogy alone carries the framing and also appears in Ch1 §1.4
2.8 Comparative Analysis | ~700 | KEEP
2.9 Research Gaps | ~900 | KEEP — but soften the absence-of-literature reliance (nobody writes about provisions applying in 2029)
2.10 Positioning | ~500 | KEEP
TARGET | ~2,000 cut | Brings Ch2 to ~9,100 and the thesis to ~80pp before figures